## Home
How to Use This Template:
Step One: Use the first tab to list the steps and tasks that need to be completed for the product launch. Step Two: Use this tab to update progress and readiness of the campaign. Step Three: Use this tab to plan and track all social media and PR activities. Remember: You should feel free to add, remove, or adjust any columns on these tabs as you see fit.
Product Launch
Planning
Template
Marketing Hub - Marketing Software
Attract visitors through blogging, social media, ads, and more!
Get Started

## Tasks to Be Completed
Product Version or Name | Task/Deliverable/Asset | DRI/Owner | Copy finalized by (date): | Localization Status (details on which languages have been completed, if applicable) | Requires Legal Review? | With Legal Team for Review? | Signed off by Legal Team? | Date to set live | Live? | Team | Notes
Alpha - Example Row | Press release | Jen | 2019-01-01 | ES completed | NO | N/A | N/A | 2019-02-01 | N/A | Product Marketing
Alpha - Example Row | Customer alert email | Michel | 2019-01-01 | ES completed | YES | YES | IN PROGRESS | 2019-01-20 | NOT YET | Customer Marketing
Alpha - Example Row | Home page promotional video | Jeremiah | 2019-01-01 | N/A | YES | NOT YET | N/A | 2019-02-01 | NOT YET | Product Marketing
Alpha - Example Row | In-app product update | Holly | 2019-01-01 | ES completed | YES | YES | YES | 2019-02-02 | YES | Engineering
Alpha - Example Row | Product Spotlight Video | Alexandre | 2019-01-01 | N/A | YES | NOT YET | N/A | 2019-02-03 | NOT YET | Video Team

## Team Readiness - Stoplights
Last updated | Department | Team | Directly Responsible Individual | Details on Assets You're Creating | Overall Readiness | Roadblocks / Concerns | Asset Links
2019-01-01 | Marketing | Website Team | Jorge | Alter pricing page to reflect new packaging options Copywriting for home page Front-end design for redesigned pricing page | On track - in progress | None
2019-01-01 | Marketing | Social Media | Jamie | All social promotion across all platforms Copywriting for paid promotion Creative assets for social posts | Ready to go | None
2019-01-01 | Product | Mobile | Alexandre | All mobile versions of Alpha V2 features | On track - not yet begun | None
2019-01-01 | Legal | Legal | Samantha | Approval of updated: - Pricing page copy - Terms of Service - Privacy Policy | Slight concern - have not started | Awaiting pricing page copy from Website Team

## Social & PR Promo Plan
Publish Date | Publish Time | Platform | Directly responsible individual | Copy ready? | Creative ready, if applicable? | Link to draft within social tool | Publish Status
2019-02-01 | 9:00 | LinkedIn | Jamie | YES | YES |  | Not yet live
2019-02-01 | 9:00 | Instagram | Jamie | YES | YES |  | Not yet live